## Sheet2
Row Labels | Sum of Date Lapsed | Count of ID
Akshay | 312 | 10
Akshay | 27 | 3
Dhilip | 1 | 1
Hemanth | 1558 | 11
Hemanth | -3 | 2
Karthi | 828 | 8
Karthi / Akshay | 356 | 1
Karthi/Akshay | 89 | 1
M Dhilippan | 5 | 1
Pathiputtur Karthik | 5 | 1
(blank) | 629 | 11
Grand Total | 3807 | 50

## Sheet1
ID | Work Item Type | Assigned To | State | Stage | Start Date | Target Date | Date Lapsed | Remaining Time | Lead Time | Requester | Sub Department | Priority | Hold Date | Resume date | Hold days | Delays Due to Stakeholder reply
1260511 | Feature | Karthi / Akshay | Approved | Scoping | 9/25/2023 | 10/15/2023 | 356 |  |  |  |  | 2
1355467 | Feature | Karthi | Done | Done | 11/29/2023 | 12/19/2023 | 291 |  |  |  |  | 3
1447892 | Feature | Hemanth | Testing | UAT | 1/26/2024 | 2/15/2024 | 233 |  |  |  |  | 3
1477503 | Feature | Hemanth | Testing | UAT | 2/23/2024 | 3/14/2024 | 205 |  |  |  |  | 2
1478300 | Feature | Hemanth | Done | Done | 2/23/2024 | 3/14/2024 | 204 |  |  |  |  | 2
1508176 | Feature | Hemanth | Done | Done | 3/21/2024 | 2024-10-04 | 177 |  |  |  |  | 3
1527193 | Feature | Hemanth | In Progress | Requirements Pending | 2024-11-04 | 2024-01-05 | 157 |  |  |  |  | 3 | 2024-08-25
1540044 | Feature | Hemanth | In Progress | WIP | 4/23/2024 | 5/13/2024 | 145 |  |  |  |  | 2
1563727 | Feature | Karthi | Testing | UAT | 5/17/2024 | 2024-06-06 | 121 |  |  |  |  | 2
1588060 | Feature | Karthi | Testing | UAT | 2024-11-06 | 2024-01-07 | 95 |  |  |  |  | 3
1591517 | Feature | Karthi | In Progress | Received requirements | 6/15/2024 | 2024-05-07 | 92 |  |  |  |  | 3
1621019 | Feature | Akshay | In Progress | Hold | 7/18/2024 | 2024-07-08 | 59 |  |  |  |  | 2 | 2024-09-21
1517963 | Feature |  | Approved |  | 2024-02-04 | 4/22/2024 | 166 |  |  |  |  | 3
1584699 | Feature |  | Approved |  | 2024-07-06 | 6/27/2024 | 100 |  |  |  |  | 3
1584702 | Feature | Hemanth | Approved | Scoping | 2024-07-06 | 6/27/2024 | 100 |  |  |  |  | 3
1584705 | Feature |  | Approved |  | 2024-07-06 | 6/27/2024 | 100 |  |  |  |  | 3
1594192 | Feature | Karthi/Akshay | In Progress | WIP | 6/18/2024 | 2024-08-07 | 89 |  |  |  |  | 2 | 9/18/2024 | 2024-09-30
1596220 | Feature | Akshay | Done | Done | 6/20/2024 | 2024-10-07 | 87 |  |  |  |  | 2
1596959 | Feature |  | Approved |  | 6/20/2024 | 2024-10-07 | 86 |  |  |  |  | 3
1606526 | Feature | Akshay | In progress | Hold | 2024-02-07 | 7/22/2024 | 75 |  |  |  |  | 2 | 2024-09-30
1624603 | Feature |  | Approved |  | 7/22/2024 | 2024-11-08 | 54 |  |  |  |  | 2
1624912 | Feature | Karthi | Done | Done | 7/23/2024 | 2024-12-08 | 54 |  |  |  |  | 2
1625037 | Feature | Akshay | Testing | UAT | 7/23/2024 | 2024-12-08 | 54 |  |  |  |  | 3
1636480 | Feature | Hemanth | Done |  | 2024-02-08 | 8/22/2024 | 43 |  |  |  |  | 4
1642539 | Feature |  | Approved | Preparing BRD | 2024-09-08 | 8/29/2024 | 36 |  |  |  |  | 3
1647291 | Feature | Hemanth | Done | Done | 8/14/2024 | 2024-03-09 | 32 |  |  |  |  | 1
1430669 | Feature | Hemanth | In Progress | Pre UAT | 2024-06-01 | 1/26/2024 | 253 |  |  |  |  | 3
1549284 | Feature | Karthi | Testing | UAT | 2024-01-05 | 5/21/2024 | 136 |  |  |  |  | 3
1661141 | Feature | Karthi | Testing | UAT | 8/24/2024 | 9/13/2024 | 22 |  |  |  |  | 2
1596155 | Feature |  | Done | Done | 6/19/2024 | 2024-09-07 | 87 |  |  |  |  | 2
1674208 | Feature |  | Done | Done | 2024-06-09 | 9/26/2024 | 8 |  |  |  |  | 3
1676416 | Feature | Akshay | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 2
1676421 | Feature | Pathiputtur Karthik | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 2
1676422 | Feature | Akshay | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 2
1676423 | Feature | Akshay | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 3
1676424 | Feature | Akshay | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 2
1676425 | Feature | Akshay | Done | Done | 2024-09-09 | 9/29/2024 | 5 |  |  |  |  | 2
1677610 | Feature | M Dhilippan | Done | Done | 2024-10-09 | 9/30/2024 | 5 |  |  |  |  | 3
1680726 | Feature | Akshay | In Progress | Pre UAT | 2024-12-09 | 9/18/2024 | 17 |  |  |  |  | 1 | 2024-09-25 | 2024-10-01
1680735 | Feature | Karthi | Done | Done | 2024-12-09 | 9/18/2024 | 17 |  |  |  |  | 1
1667352 | Feature | Akshay | Testing | Pre UAT | 8/29/2024 | 9/18/2024 | 17 |  |  |  |  | 3
1681576 | Feature | Hemanth | In Progress | Hold | 9/18/2024 | 2024-08-10 | -3 |  |  |  |  | 2 | 2024-02-10
1685624 | Feature |  | Approved | Scoping | [7 empty] | 3
1692200 | Feature |  | Approved | Scoping | 9/23/2024 | 10/13/2024 | -8 |  |  |  |  | 2
1692141 | Feature | Hemanth | Done | Done | 9/23/2024 | 9/26/2024 | 9 |  |  |  |  | 2 |  |  |  | appericated for the work which we goven till noew
1694662 | Feature | Dhilip | Done | Done | 9/25/2024 | 9/26/2024 | 1 |  | 1 |  |  | 3
1697035 | Feature |  | New | Scoping | [7 empty] | 2
1694875 | Feature | Akshay | Done | Done | 9/25/2024 | 9/30/2024 | 5 |  | 5 |  |  | 4
1702067 | Feature | Akshay | In Progress | WIP | 2024-01-10 | [6 empty] | 3
1702254 | Feature | Hemanth | In Progress | WIP | 2024-10-01 | [6 empty] | 1